## DEPLOYMENT PLAN
DEPLOYMENT PLAN DIGIRO
Task | Start date & time | Finish date & time | Owner | Status
Penentuan Ruang Lingkup | 2026-04-03 | 2026-11-03 | Dede Amelia | Completed
Analisis Kebutuhan Pengguna | 2026-11-03 | 03/18/2026 | Dede Amelia | Completed
Penyusunan Jadwal & Anggaran | 03/18/2026 | 03/25/2026 | Dede Amelia | Completed
Studi Kelayakan Teknis | 03/18/2026 | 03/25/2026 | Dede Amelia | Completed
Perancangan Alur Kerja (User Flow) | 03/25/2026 | 2026-01-04 | Gifta Ananda | Completed
Perancangan Alur Kerja (User Flow) | 03/25/2026 | 2026-01-04 | Gifta Ananda | Completed
Pembuatan Wireframe | 03/25/2026 | 2026-01-04 | Luthfiyah R | Completed
Desain High-Fidelity (Mockup) | 2026-01-04 | 2026-08-04 | Luthfiyah R | Completed
Pembuatan Prototype | 2026-01-04 | 2026-08-04 | Luthfiyah R | Completed
Back-End (Logika Sistem) | 2026-08-04 | 04/15/2026 | Ariq Gusmila | Completed
Front-End (Antarmuka Pengguna) | 04/15/2026 | 04/22/2026 | Ariq Gusmila | Completed
Database & Integrasi | 04/15/2026 | 04/22/2026 | Ariq Gusmila | Completed
Input Data Master | 04/15/2026 | 04/22/2026 | Ariq Gusmila | Completed
Digitalisasi Dokumen | 04/15/2026 | 04/22/2026 | Ariq Gusmila | Completed
Pengaturan Kategori | 04/15/2026 | 04/22/2026 | Ariq Gusmila | Completed
Unit Testing | 04/29/2026 | 2026-05-06 | Nawap | Completed
System Integration Testing (SIT) | 04/29/2026 | 2026-05-06 | Nawap | Completed
User Acceptance Test (UAT) | 04/29/2026 | 2026-05-06 | Nawap | Completed
Bug Fixing | 04/29/2026 | 2026-05-06 | Nawap | At risk
Konfigurasi Hosting & Domain | 2026-03-06 | 2026-10-06 | Ariq Gusmila | Completed
Pelatihan Admin (Pustakawan) | 2026-03-06 | 2026-10-06 | Dede Amelia | Completed
Go-Live | 2026-03-06 | 2026-10-06 | Dede Amelia | Completed
Penyerahan Dokumentasi | 2026-03-06 | 2026-10-06 | Dede Amelia | Completed